GMP CSV Controlled Document

Data Migration Strategy and Plan

QCLabOne 2.0 QC Laboratory Digital Platform Replacement Project

| Control Field | Value |
| --- | --- |
| Document number | QCL-2026-DMP-001 |
| System | QCLabOne 2.0 LIMS/LES |
| Lifecycle phase | Data Migration |
| Version | 1.0 |
| Effective/record date | 2026-10-31 |
| Status | Approved in fictional case |

Use notice: This Markdown file is a fully populated fictional CSV training case. It is not an executed GMP record and does not replace company procedures, approved signatures, supplier evidence, or site-specific risk decisions.

# Document control

| Field | Value |
| --- | --- |
| Document number | QCL-2026-DMP-001 |
| Company | NovaSterile Pharma Co., Ltd. |
| Site | Suzhou Sterile Products Manufacturing Site |
| Project | QCLabOne 2.0 QC Laboratory Digital Platform Replacement Project |
| System | QCLabOne 2.0 LIMS/LES |
| Lifecycle phase | Data Migration |
| Version | 1.0 |
| Effective/record date | 2026-10-31 |
| Case status | Approved in fictional case |

# Governing references

China GMP (2010 Revision), Appendix: Computerised Systems (effective 1 December 2015)

China GMP (2010 Revision), Appendix: Qualification and Validation (effective 1 December 2015)

EU GMP Annex 11: Computerised Systems (2011)

EU GMP Annex 15: Qualification and Validation (2015)

21 CFR Part 11: Electronic Records; Electronic Signatures

FDA Guidance: Part 11, Electronic Records; Electronic Signatures — Scope and Application

PIC/S PI 041-1: Good Practices for Data Management and Integrity in Regulated GMP/GDP Environments (2021)

ISPE GAMP 5, Second Edition (2022), used as non-binding industry guidance

# 1. Migration objectives

Move active/required legacy data into QCLabOne and retain remaining historical records in ArchiveVault without loss of meaning, relationships, metadata, audit trail or retrievability.

# 2. Scope and disposition

| Source | Volume | Disposition |
| --- | --- | --- |
| Legacy LIMS samples | 86,742 | 2018–cutover active/required records migrated; all records archived |
| Legacy LIMS results | 326,115 | Associated active records migrated; all results archived |
| Attachments | 24,806 | Migrated or archived with SHA-256 checksum |
| Active stability pulls | 1,984 | Migrated with schedules and history |
| Stability/reagent/EM spreadsheets | 12 controlled workbooks | Active data migrated after profiling; source preserved |
| Selected paper indexes | 3 indexes / 9,420 images | Index and approved image set archived; paper remains per retention |

# 3. Migration phases

1. Source freeze/profile. 2. Mapping and transformation approval. 3. Trial migration 1—technical completeness. 4. Cleansing and rule refinement. 5. Trial migration 2—business/UAT and performance. 6. Production extraction and freeze. 7. Load, reconciliation and exception disposition. 8. Business/QA acceptance. 9. Legacy read-only period and final archive verification.

# 4. Acceptance criteria

Source/target counts reconcile 100% or have approved explained exclusions.

Critical fields for migrated active records are checked 100%.

A statistically justified sample of noncritical fields meets ≥99.5% accuracy, with no systemic defect.

Attachments reconcile by count and checksum.

Parent/child relationships and audit histories pass defined checks.

No critical/high migration exception remains before go-live.

# 5. Security and source protection

Extraction uses read-only accounts and encrypted transfer. Source backups are retained. Production source is frozen during final migration except approved emergency transactions, which are separately reconciled.

Each trial migration has a formal entry and exit decision. Trial 1 validates technical extraction/loading and identifies profiling issues. Trial 2 validates approved mapping, cleansing rules and reconciliation approach. Final migration may start only after open critical/high exceptions are closed, source freeze is confirmed, rollback criteria are agreed and business owners accept residual migration risk.

| Migration gate | Exit evidence |
| --- | --- |
| Profiling complete | Source counts, data-quality issues and mapping gaps documented |
| Trial migration 1 | Load path proven and major technical issues logged |
| Trial migration 2 | Mapping baseline, reconciliation report and exception disposition accepted |
| Final migration readiness | Freeze plan, rollback plan, trained team and approval to proceed |
| Post-migration acceptance | Counts, critical fields, relationships, attachments and retrieval accepted |

# 6. Related documents

| Relationship | Document ID | Document |
| --- | --- | --- |
| Input | QCL-2026-SCP-001 | [QCLabOne 2.0 Project Scope Statement](006_Project_Scope_Statement.md) |
| Input | QCL-2026-DIRA-001 | [Data Integrity Risk Assessment](012_Data_Integrity_Risk_Assessment.md) |
| Input | QCL-2026-URS-001 | [User Requirements Specification](022_User_Requirements_Specification.md) |
| Input | QCL-2026-DDS-001 | [Data Flow, Data Dictionary and Metadata Specification](028_Data_Flow_Data_Dictionary_and_Metadata_Specification.md) |
| Output | QCL-2026-DMS-001 | [Data Mapping, Cleansing and Transformation Specification](037_Data_Mapping_Cleansing_and_Transformation_Specification.md) |
| Output | QCL-2026-FRA-001 | [Functional Risk Assessment](038_Functional_Risk_Assessment.md) |
| Output | QCL-2026-DMT-001 | [Data Migration Test and Reconciliation Report](052_Data_Migration_Test_and_Reconciliation_Report.md) |
| Output | QCL-2026-DEV-001 | [Validation Deviation Log and Investigation Report](061_Validation_Deviation_Log_and_Investigation_Report.md) |
| Output | QCL-2026-PDM-001 | [Production Data Migration Execution and Reconciliation Record](073_Production_Data_Migration_Execution_and_Reconciliation_Record.md) |
| Output | QCL-2028-LAR-001 | [Legacy Data Archiving and Retention Plan](102_Legacy_Data_Archiving_and_Retention_Plan.md) |
| Output | QCL-2028-AVR-001 | [Legacy Archive Verification and Retrievability Report](103_Legacy_Archive_Verification_and_Retrievability_Report.md) |

# Approval record

| Approval step | Role | Case outcome |
| --- | --- | --- |
| Prepared by | Data Migration Lead | Completed |
| Reviewed by | QC Data Owner | Completed |
| Approved by | QA CSV Lead | Approved in fictional case |

# Revision history

| Version | Date | Change |
| --- | --- | --- |
| 1.0 | 2026-10-31 | Initial approved fictional case version. |